## Phase wise implementation
Technology Used | Phase 1 Implementation Identity + Device Foundation | Phase 2 Implementation Secure Access + Workload Protection | Phase 3 Implementation Detection + Response (SOC) | Security Significance | Zero Trust Principle | Attack Mitigation
Microsoft Entra ID | Identity platform with MFA, passwordless (Windows Hello + FIDO2), Conditional Access baseline | Authentication for App Proxy apps, risk-based CA | Signin & audit logs in SIEM | Central identity provider for secure authentication | Verify Explicitly | Prevents credential theft, phishing, unauthorized access
Microsoft Entra Privileged Identity Management | JIT access, approval-based role activation | Time-bound privileged access for app admins | PIM activity monitored in SIEM | Eliminates standing admin access | Least Privilege | Prevents privilege escalation, insider abuse
Windows Autopilot | Zero-touch provisioning, Entra join, Intune enrollment | Provisioned devices used for secure access | Provisioning logs (optional monitoring) | Secure and automated device onboarding | Verify Device Trust | Prevents unmanaged device access
Microsoft Intune | Compliance policies, security baselines, patching | Device compliance required for app access | Compliance logs in SIEM | Ensures only compliant devices access resources | Verify Device Trust | Prevents compromised/unpatched device access
Microsoft Defender for Endpoint | EDR, threat protection, behavioral monitoring | Device risk signals integrated with CA | Threat alerts ingested into SIEM | Advanced endpoint threat detection | Assume Breach | Detects malware, ransomware, zero-day attacks
Microsoft Defender for Business | Endpoint security for SMB workloads | Supports endpoint protection in access decisions | Alerts integrated into SIEM | Endpoint protection and monitoring | Assume Breach | Prevents endpoint compromise
Windows Hello for Business | Passwordless authentication setup (PIN/biometric) | Used for secure SSO login | Auth logs monitored | Phishing-resistant authentication | Verify Explicitly | Prevents credential theft, replay attacks
FIDO2 Security Keys | Strong authentication for privileged users | Secures admin access | Auth events logged | Hardware-based authentication | Verify Explicitly | Prevents phishing, credential replay
Microsoft Entra Application Proxy | Implemented in later phase | Secure publishing of internal apps | App access logs monitored | Remote access without VPN | Verify Explicitly | Prevents direct network exposure
Microsoft Defender for Cloud Apps | CASB monitoring for M365 | Session control for app usage | CASB alerts in SIEM | Monitors cloud activity & data access | Assume Breach | Prevents data exfiltration, detects anomalies
Microsoft SharePoint Online | Secure document storage | Controlled access via CA | File activity logs monitored | Secure collaboration platform | Least Privilege | Prevents unauthorized data access
Microsoft 365 (Unified Audit Logs) | Audit logging enabled | Continued monitoring | Unified logs in SIEM | Central audit visibility | Assume Breach | Detects suspicious activity across services
Microsoft Azure | Cloud platform foundation | VM hosting internal application | Activity logs in SIEM | Infrastructure layer security | Assume Breach | Detects unauthorized resource changes
Azure Firewall | Basic network security setup | Egress & ingress traffic control | Firewall logs in SIEM | Central traffic control and filtering | Assume Breach | Prevents data exfiltration, command & control traffic
Network Security Groups (NSG) | Subnet-level segmentation | Traffic filtering between tiers | NSG flow logs monitored | Micro-segmentation of network | Assume Breach | Prevents lateral movement
Private Endpoints | Secure service access | Used for Key Vault and Storage with private access | Access logs monitored | Eliminates public exposure | Verify Explicitly | Prevents data exposure over internet
Azure Key Vault | Secure secrets storage | Access via Managed Identity | Audit logs in SIEM | Protects secrets and keys | Least Privilege | Prevents secret leakage
Managed Identity | Identity for Azure resources | Used for secure service access | Access logs monitored | Eliminates hardcoded credentials | Least Privilege | Prevents credential exposure
Azure Storage | Secure storage account | Public access disabled, private access | Access logs monitored | Secure data storage | Least Privilege | Prevents unauthorized data access
Microsoft Sentinel | Implemented in later phase | Implemented in later phase | SIEM + SOAR implementation | Threat detection and response platform | Assume Breach | Detects and responds to attacks
Log Analytics Workspace | Implemented in later phase | Log collection foundation | Central log storage | Enables KQL and monitoring | Assume Breach | Supports detection and investigation
Azure Policy | Governance baseline | Enforces security controls | Resource compliance monitored | Prevents misconfigurations | Verify Explicitly | Prevents insecure deployments
Conditional Access | Baseline policies | Risk + device-based policies | Logs monitored in SIEM | Controls access dynamically | Verify Explicitly | Prevents unauthorized access
Continuous Access Evaluation (CAE) | Implemented in later phase | Session-level enforcement | Session logs monitored | Real-time access control | Verify Explicitly | Stops session hijacking
Attack Simulation & Validation | Implemented in later phase | Basic attack simulations performed | Detection validated via SIEM | Validates effectiveness of security controls | Assume Breach | Ensures detection and response capabilities are working
Azure Diagnostic Settings | Logging enabled for all resources | Integrated with Log Analytics | Data available in SIEM | Ensures visibility across all services | Assume Breach | Enables detection and forensic investigation
Entra ID Risk Policies | Baseline risk detection | Risk-based Conditional Access enforced | Risk events monitored in SIEM | Dynamic access control based on risk | Verify Explicitly | Prevents compromised account access

## GreenField Deployment
Phase | Week | Day | Down Time | Task Category | Task Name | Description | Tool / Service | Owner | Priority | Status | Dependencies | Notes
Pre-requisite | Tenant Setup | Day 1 | None | Tenant Creation | Create Microsoft 365 Tenant | Register organization tenant | Microsoft 365 Admin Center | Cloud Admin | High | Pending | None | Primary tenant setup
Pre-requisite | Tenant Setup | Day 1 | None | Domain Configuration | Add Custom Domain | Add company domain to tenant | Microsoft Entra ID | Cloud Admin | High | Pending | Tenant Created | Verify DNS records
Pre-requisite | Tenant Setup | Day 1 | None | Domain Verification | Verify Domain Ownership | Validate DNS TXT record | Microsoft Entra ID | Cloud Admin | High | Pending | Domain Added
Pre-requisite | Tenant Setup | Day 1 | None | DNS Configuration | Add MX Record | Route company email to Microsoft 365 | Exchange Online / DNS Provider | Cloud Admin | High | Pending | Domain Verified | Required for email delivery
Pre-requisite | Tenant Setup | Day 1 | None | DNS Configuration | Add Autodiscover Record | Enable Outlook automatic configuration | Exchange Online / DNS Provider | Cloud Admin | High | Pending | Domain Verified | Supports Outlook connectivity
Pre-requisite | Tenant Setup | Day 1 | None | Email Security | Add SPF Record | Prevent email spoofing | DNS Provider | Security Admin | High | Pending | Domain Verified | Sender Policy Framework
Pre-requisite | Tenant Setup | Day 1 | None | Email Security | Enable DKIM Signing | Configure DKIM email authentication | Exchange Online | Security Admin | Medium | Pending | SPF Configured | Improves email trust
Pre-requisite | Tenant Setup | Day 1 | None | Email Security | Configure DMARC Policy | Protect domain from phishing attacks | DNS Provider | Security Admin | Medium | Pending | DKIM Configured | Email protection policy
Pre-requisite | Tenant Setup | Day 1 | None | Identity Security | Create Users | Provision company users | Microsoft Entra ID | Cloud Admin | High | Pending | Tenant Ready | New employees added
Pre-requisite | Tenant Setup | Day 1 | None | Licensing | Assign Microsoft 365 E5 Licenses | Upload or assign licenses | Microsoft 365 Admin Center | Cloud Admin | High | Pending | Tenant Ready
Pre-requisite | Tenant Setup | Day 2 | None | Security Baseline | Create Break Glass Accounts | Create emergency admin accounts | Microsoft Entra ID | Security Admin | High | Pending | Tenant Ready | Exclude from CA
Pre-requisite | Tenant Setup | Day 2 | None | Audit Setup | Enable Unified Audit Logs | Enable Microsoft 365 audit logging | Microsoft Purview | Security Admin | High | Pending | Tenant Ready
Pre-requisite | Tenant Setup | Day 2 | None | Security Setup | Enable Security Defaults / Baseline | Apply baseline security configuration | Microsoft Entra ID | Security Admin | High | Pending | Tenant Ready
Phase 1 | Week 1 | Day 1 | None | Identity Security | Configure MFA Policy | Enable MFA for all users | Microsoft Entra ID | Security Admin | High | Pending | Tenant Setup
Phase 1 | Week 1 | Day 1 | None | Identity Security | Block Legacy Authentication | Disable IMAP/POP Basic Auth | Microsoft Entra ID | Security Admin | High | Pending | MFA Configured
Phase 1 | Week 1 | Day 2 | None | Identity Security | Configure Conditional Access | Create baseline CA policies | Microsoft Entra ID | Security Admin | High | Pending | MFA Enabled
Phase 1 | Week 1 | Day 3 | None | Device Management | Enable Intune MDM Authority | Activate device management | Microsoft Intune | Endpoint Admin | High | Pending | Tenant Setup
Phase 1 | Week 1 | Day 3 | None | Device Management | Configure Enrollment Restrictions | Restrict device enrollment types | Microsoft Intune | Endpoint Admin | Medium | Pending | Intune Enabled | Prevent unauthorized device enrollment
Phase 1 | Week 1 | Day 3 | None | Device Management | Configure Device Platform Restrictions | Allow only Windows corporate devices | Microsoft Intune | Endpoint Admin | Medium | Pending | Intune Enabled | Block unsupported platforms
Phase 1 | Week 1 | Day 3 | None | Compliance | Create Device Compliance Policy | Define compliance rules | Microsoft Intune | Endpoint Admin | High | Pending | Intune Enabled
Phase 1 | Week 1 | Day 4 | None | Security Baseline | Deploy Security Baseline | Apply endpoint security baseline | Microsoft Intune | Endpoint Admin | High | Pending | Intune Enabled
Phase 1 | Week 1 | Day 5 | None | Autopilot Setup | Create Autopilot Profile | Configure zero-touch provisioning | Windows Autopilot | Endpoint Admin | High | Pending | Intune Enabled
Phase 1 | Week 2 | Day 1 | None | Device Enrollment | Register Devices | Upload hardware hash | Windows Autopilot | Endpoint Admin | High | Pending | Autopilot Profile
Phase 1 | Week 2 | Day 2 | None | Endpoint Security | Deploy Defender Policies | Configure EDR rules | Microsoft Defender for Endpoint | Security Admin | High | Pending | Intune Ready
Phase 1 | Week 2 | Day 2 | None | Endpoint Security | Onboard Devices to Defender | Connect endpoints to security monitoring | Microsoft Defender for Endpoint | Security Admin | High | Pending | Intune Ready | Enable endpoint detection
Phase 1 | Week 2 | Day 2 | None | Endpoint Security | Enable Threat & Vulnerability Management | Monitor device vulnerabilities | Microsoft Defender for Endpoint | Security Admin | Medium | Pending | Defender Onboarded | Vulnerability insights
Phase 1 | Week 2 | Day 3 | None | Data Storage | Create SharePoint Team Site | Create company document repository | SharePoint Online | SharePoint Admin | High | Pending | Tenant Ready
Phase 1 | Week 2 | Day 3 | None | Data Security | Configure External Sharing Policies | Disable public sharing | SharePoint Online | SharePoint Admin | Medium | Pending | Site Created
Phase 1 | Week 2 | Day 4 | None | File Sync | Configure OneDrive Silent Sign-In | Auto configure user sync | Microsoft Intune | Endpoint Admin | Medium | Pending | Intune Ready
Phase 1 | Week 2 | Day 5 | None | Data Protection | Configure DLP Policies | Protect sensitive information | Microsoft Purview | Security Admin | High | Pending | SharePoint Ready
Phase 1 | Week 2 | Day 5 | None | Information Protection | Create Sensitivity Labels | Classify documents | Microsoft Purview | Security Admin | Medium | Pending | DLP Configured
Phase 1 | Week 2 | Day 5 | None | Security Validation | Test Conditional Access Policies | Validate access restrictions | Microsoft Entra ID | Security Admin | Medium | Pending | CA Policies Created | Pilot testing with test users
Phase 2 | Week 3 | Day 1 | None | Cloud Infrastructure | Create Azure VM | Deploy internal application server | Microsoft Azure | Cloud Admin | High | Pending | Tenant Ready
Phase 2 | Week 3 | Day 2 | None | Application Setup | Install Web Server | Deploy IIS/NGINX | Application Server | Infra Admin | High | Pending | VM Created
Phase 2 | Week 3 | Day 3 | None | Application Access | Install Application Proxy Connector | Enable internal app publishing | Microsoft Entra Application Proxy | Cloud Admin | High | Pending | Server Ready
Phase 2 | Week 3 | Day 4 | None | Application Publishing | Publish Internal Application | Create secure external URL | Microsoft Entra ID | Cloud Admin | High | Pending | Connector Installed
Phase 2 | Week 3 | Day 5 | None | Security Policy | Apply Conditional Access | App specific security policy | Microsoft Entra ID | Security Admin | High | Pending | App Published
Phase 2 | Week 3 | Day 5 | None | Session Control | Enable CASB Session Monitoring | Monitor app access activity | Microsoft Defender for Cloud Apps | Security Admin | Medium | Pending | App Published
Phase 3 | Week 4 | Day 1 | None | SIEM Deployment | Create Log Analytics Workspace | Prepare SIEM backend | Microsoft Azure | Cloud Admin | High | Pending | Tenant Ready
Phase 3 | Week 4 | Day 1 | None | SIEM Setup | Enable Microsoft Sentinel | Activate SIEM monitoring | Microsoft Sentinel | Security Admin | High | Pending | Workspace Created
Phase 3 | Week 4 | Day 2 | None | Log Integration | Connect Entra Logs | Import identity logs | Microsoft Sentinel | Security Admin | High | Pending | Sentinel Enabled
Phase 3 | Week 4 | Day 2 | None | Log Integration | Connect Defender Logs | Import endpoint alerts | Microsoft Sentinel | Security Admin | High | Pending | Sentinel Enabled
Phase 3 | Week 4 | Day 3 | None | Log Integration | Connect Microsoft 365 Logs | Import SharePoint and Exchange logs | Microsoft Sentinel | Security Admin | High | Pending | Sentinel Enabled
Phase 3 | Week 4 | Day 4 | None | Threat Detection | Create Analytics Rules | Configure detection rules | Microsoft Sentinel | Security Admin | High | Pending | Logs Connected
Phase 3 | Week 4 | Day 5 | None | SOAR Automation | Create Incident Playbooks | Automate response actions | Microsoft Sentinel | Security Admin | Medium | Pending | Analytics Rules
Phase 3 | Week 4 | Day 5 | None | Monitoring | Create SOC Dashboard | Visualize security metrics | Microsoft Sentinel | Security Admin | Medium | Pending | SIEM Ready

## BrownField Deployment
Phase | Week | Day | Down Time | Task Category | Task Name | Description | Tool / Service | Owner | Priority | Status | Dependencies | Notes
Pre-requisite | Tenant Setup | Day 1 | None | Tenant Creation | Create Microsoft 365 Tenant | Register organization tenant | Microsoft 365 Admin Center | Cloud Admin | High | Pending | None | Primary tenant setup
Pre-requisite | Tenant Setup | Day 1 | None | Domain Configuration | Add Custom Domain | Add company domain to tenant | Microsoft Entra ID | Cloud Admin | High | Pending | Tenant Created | Verify DNS records
Pre-requisite | Tenant Setup | Day 1 | None | Domain Verification | Verify Domain Ownership | Validate DNS TXT record | Microsoft Entra ID | Cloud Admin | High | Pending | Domain Added
Pre-requisite | Tenant Setup | Day 1 | None | DNS Configuration | Add MX Record | Route company email to Microsoft 365 | Exchange Online / DNS Provider | Cloud Admin | High | Pending | Domain Verified | Required for email delivery
Pre-requisite | Tenant Setup | Day 1 | Yes | DNS Configuration | Update MX Record | Route company email to Microsoft 365 | Exchange Online / DNS Provider | Cloud Admin | High | Pending | Domain Verified | Email downtime expected
Pre-requisite | Tenant Setup | Day 1 | None | DNS Configuration | Add Autodiscover Record | Enable Outlook automatic configuration | Exchange Online / DNS Provider | Cloud Admin | High | Pending | Domain Verified | Supports Outlook connectivity
Pre-requisite | Tenant Setup | Day 1 | None | Email Security | Add SPF Record | Prevent email spoofing | DNS Provider | Security Admin | High | Pending | Domain Verified | Sender Policy Framework
Pre-requisite | Tenant Setup | Day 1 | None | Email Security | Enable DKIM Signing | Configure DKIM email authentication | Exchange Online | Security Admin | Medium | Pending | SPF Configured | Improves email trust
Pre-requisite | Tenant Setup | Day 1 | None | Email Security | Configure DMARC Policy | Protect domain from phishing attacks | DNS Provider | Security Admin | Medium | Pending | DKIM Configured | Email protection policy
Pre-requisite | Tenant Setup | Day 1 | None | Identity Security | Create Users | Provision company users | Microsoft Entra ID | Cloud Admin | High | Pending | Tenant Ready | New employees added
Pre-requisite | Tenant Setup | Day 1 | None | Licensing | Assign Microsoft 365 E5 Licenses | Upload or assign licenses | Microsoft 365 Admin Center | Cloud Admin | High | Pending | Tenant Ready
Pre-requisite | Tenant Setup | Day 2 | None | Security Baseline | Create Break Glass Accounts | Create emergency admin accounts | Microsoft Entra ID | Security Admin | High | Pending | Tenant Ready | Exclude from CA
Pre-requisite | Tenant Setup | Day 2 | None | Audit Setup | Enable Unified Audit Logs | Enable Microsoft 365 audit logging | Microsoft Purview | Security Admin | High | Pending | Tenant Ready
Pre-requisite | Tenant Setup | Day 2 | None | Security Setup | Enable Security Defaults / Baseline | Apply baseline security configuration | Microsoft Entra ID | Security Admin | High | Pending | Tenant Ready
Pre-requisite | Tenant Setup | Day 2 | Yes | Email Migration | Migrate Existing Mailboxes | Migrate current users to Exchange Online | Exchange Online / Migration Tool | Cloud Admin | High | Pending | MX Updated | Temporary email downtime expected
Phase 1 | Week 1 | Day 1 | None | Identity Security | Configure MFA Policy | Enable MFA for all users | Microsoft Entra ID | Security Admin | High | Pending | Tenant Setup
Phase 1 | Week 1 | Day 1 | None | Identity Security | Block Legacy Authentication | Disable IMAP/POP Basic Auth | Microsoft Entra ID | Security Admin | High | Pending | MFA Configured
Phase 1 | Week 1 | Day 2 | None | Identity Security | Configure Conditional Access | Create baseline CA policies | Microsoft Entra ID | Security Admin | High | Pending | MFA Enabled
Phase 1 | Week 1 | Day 3 | None | Device Management | Enable Intune MDM Authority | Activate device management | Microsoft Intune | Endpoint Admin | High | Pending | Tenant Setup
Phase 1 | Week 1 | Day 3 | None | Device Management | Configure Enrollment Restrictions | Restrict device enrollment types | Microsoft Intune | Endpoint Admin | Medium | Pending | Intune Enabled | Prevent unauthorized device enrollment
Phase 1 | Week 1 | Day 3 | None | Device Management | Configure Device Platform Restrictions | Allow only Windows corporate devices | Microsoft Intune | Endpoint Admin | Medium | Pending | Intune Enabled | Block unsupported platforms
Phase 1 | Week 1 | Day 3 | None | Compliance | Create Device Compliance Policy | Define compliance rules | Microsoft Intune | Endpoint Admin | High | Pending | Intune Enabled
Phase 1 | Week 1 | Day 4 | None | Security Baseline | Deploy Security Baseline | Apply endpoint security baseline | Microsoft Intune | Endpoint Admin | High | Pending | Intune Enabled
Phase 1 | Week 1 | Day 5 | None | Autopilot Setup | Create Autopilot Profile | Configure zero-touch provisioning | Windows Autopilot | Endpoint Admin | High | Pending | Intune Enabled
Phase 1 | Week 2 | Day 1 | None | Device Enrollment | Register Devices | Upload hardware hash | Windows Autopilot | Endpoint Admin | High | Pending | Autopilot Profile
Phase 1 | Week 2 | Day 2 | None | Endpoint Security | Deploy Defender Policies | Configure EDR rules | Microsoft Defender for Endpoint | Security Admin | High | Pending | Intune Ready
Phase 1 | Week 2 | Day 2 | None | Endpoint Security | Onboard Devices to Defender | Connect endpoints to security monitoring | Microsoft Defender for Endpoint | Security Admin | High | Pending | Intune Ready | Enable endpoint detection
Phase 1 | Week 2 | Day 2 | None | Endpoint Security | Enable Threat & Vulnerability Management | Monitor device vulnerabilities | Microsoft Defender for Endpoint | Security Admin | Medium | Pending | Defender Onboarded | Vulnerability insights
Phase 1 | Week 2 | Day 3 | None | Data Storage | Create SharePoint Team Site | Create company document repository | SharePoint Online | SharePoint Admin | High | Pending | Tenant Ready
Phase 1 | Week 2 | Day 3 | Yes | Data Storage | Sync Existing Data to SharePoint | Migrate current files to SharePoint | SharePoint Online / Mover / Tool | SharePoint Admin | High | Pending | Site Created | Temporary reduced access expected
Phase 1 | Week 2 | Day 3 | None | Data Security | Configure External Sharing Policies | Disable public sharing | SharePoint Online | SharePoint Admin | Medium | Pending | Site Created
Phase 1 | Week 2 | Day 4 | None | File Sync | Configure OneDrive Silent Sign-In | Auto configure user sync | Microsoft Intune | Endpoint Admin | Medium | Pending | Intune Ready
Phase 1 | Week 2 | Day 5 | None | Data Protection | Configure DLP Policies | Protect sensitive information | Microsoft Purview | Security Admin | High | Pending | SharePoint Ready
Phase 1 | Week 2 | Day 5 | None | Information Protection | Create Sensitivity Labels | Classify documents | Microsoft Purview | Security Admin | Medium | Pending | DLP Configured
Phase 1 | Week 2 | Day 5 | None | Security Validation | Test Conditional Access Policies | Validate access restrictions | Microsoft Entra ID | Security Admin | Medium | Pending | CA Policies Created | Pilot testing with test users
Phase 2 | Week 3 | Day 1 | None | Cloud Infrastructure | Create Azure VM | Deploy internal application server | Microsoft Azure | Cloud Admin | High | Pending | Tenant Ready
Phase 2 | Week 3 | Day 2 | None | Application Setup | Install Web Server | Deploy IIS/NGINX | Application Server | Infra Admin | High | Pending | VM Created
Phase 2 | Week 3 | Day 3 | None | Application Access | Install Application Proxy Connector | Enable internal app publishing | Microsoft Entra Application Proxy | Cloud Admin | High | Pending | Server Ready
Phase 2 | Week 3 | Day 4 | None | Application Publishing | Publish Internal Application | Create secure external URL | Microsoft Entra ID | Cloud Admin | High | Pending | Connector Installed
Phase 2 | Week 3 | Day 5 | None | Security Policy | Apply Conditional Access | App specific security policy | Microsoft Entra ID | Security Admin | High | Pending | App Published
Phase 2 | Week 3 | Day 5 | None | Session Control | Enable CASB Session Monitoring | Monitor app access activity | Microsoft Defender for Cloud Apps | Security Admin | Medium | Pending | App Published
Phase 3 | Week 4 | Day 1 | None | SIEM Deployment | Create Log Analytics Workspace | Prepare SIEM backend | Microsoft Azure | Cloud Admin | High | Pending | Tenant Ready
Phase 3 | Week 4 | Day 1 | None | SIEM Setup | Enable Microsoft Sentinel | Activate SIEM monitoring | Microsoft Sentinel | Security Admin | High | Pending | Workspace Created
Phase 3 | Week 4 | Day 2 | None | Log Integration | Connect Entra Logs | Import identity logs | Microsoft Sentinel | Security Admin | High | Pending | Sentinel Enabled
Phase 3 | Week 4 | Day 2 | None | Log Integration | Connect Defender Logs | Import endpoint alerts | Microsoft Sentinel | Security Admin | High | Pending | Sentinel Enabled
Phase 3 | Week 4 | Day 3 | None | Log Integration | Connect Microsoft 365 Logs | Import SharePoint and Exchange logs | Microsoft Sentinel | Security Admin | High | Pending | Sentinel Enabled
Phase 3 | Week 4 | Day 4 | None | Threat Detection | Create Analytics Rules | Configure detection rules | Microsoft Sentinel | Security Admin | High | Pending | Logs Connected
Phase 3 | Week 4 | Day 5 | None | SOAR Automation | Create Incident Playbooks | Automate response actions | Microsoft Sentinel | Security Admin | Medium | Pending | Analytics Rules
Phase 3 | Week 4 | Day 5 | None | Monitoring | Create SOC Dashboard | Visualize security metrics | Microsoft Sentinel | Security Admin | Medium | Pending | SIEM Ready

## Onboarding
Category | Task | Tool / Service | Owner | Notes
Identity | Create user account in Microsoft Entra ID | Microsoft Entra ID | Cloud Admin | Include display name, username, job title, department
| Assign appropriate licenses (M365 E5, Intune, Defender) | Microsoft 365 Admin Center | Cloud Admin | Ensure license includes email, SharePoint, Teams, Defender
| Add user to relevant security groups | Microsoft Entra ID | Security Admin | Groups control access and CA policies
Email & Communication | Provision mailbox | Exchange Online | Cloud Admin | Check MX records and routing
| Configure email signatures & policies | Exchange Online / Admin | Cloud Admin | Optional branding/signature templates
| Enable MFA & Conditional Access | Microsoft Entra ID | Security Admin | Ensure secure login from first day
Devices | Register device in Intune / Autopilot | Microsoft Intune / Windows Autopilot | Endpoint Admin | Include device compliance policy
| Deploy corporate apps via Intune | Microsoft Intune | Endpoint Admin | Teams, Outlook, OneDrive, VPN client, etc.
| Configure OneDrive Silent Sign-In | Microsoft Intune | Endpoint Admin | Ensures files are auto-synced
Data Access & Collaboration | Grant SharePoint & Teams access | SharePoint Online / Teams | SharePoint Admin | Include department or project sites
| Apply Sensitivity Labels & DLP policies | Microsoft Purview | Security Admin | Protect sensitive documents
Security & Monitoring | Onboard device to Defender for Endpoint | Microsoft Defender for Endpoint | Security Admin | Ensure device is protected and monitored
| Enable Threat & Vulnerability Management | Microsoft Defender for Endpoint | Security Admin | Scan for device vulnerabilities
| Email & App Access Logging | Microsoft Sentinel | Security Admin | Logging enabled for audit and SOC visibility
Training & Compliance | Provide IT policies & acceptable use guide | Internal Docs / SharePoint | HR / IT | Include password policies, phishing guidance
| MFA & Security Awareness Training | Microsoft Entra ID / Security Training | Security Admin | Confirm completion

## Offboarding
Category | Task | Tool / Service | Owner | Notes
Identity | Disable user account in Microsoft Entra ID | Microsoft Entra ID | Cloud Admin | Prevents login immediately
| Remove from security groups | Microsoft Entra ID | Security Admin | Ensures no access to confidential resources
| Remove licenses | Microsoft 365 Admin Center | Cloud Admin | Recover licenses for reuse
Email & Communication | Set mailbox to inactive / hold | Exchange Online | Cloud Admin | Retain mailbox data for compliance
| Configure email forwarding / auto-reply | Exchange Online | Cloud Admin | Forward to manager or archive
| Remove access to Teams & distribution lists | Microsoft Teams / Exchange | SharePoint Admin | Prevent collaboration access
Devices | Wipe corporate device (Intune / Autopilot) | Microsoft Intune | Endpoint Admin | Reset or retire device safely
| Remove device from Intune & Entra | Microsoft Intune / Entra ID | Endpoint Admin | Ensure compliance and security
Data & Collaboration | Transfer ownership of files | SharePoint / OneDrive | SharePoint Admin | Assign manager or team member as owner
| Backup / archive emails and SharePoint data | Exchange Online / SharePoint Online | Cloud Admin | Compliance and audit purposes
| Revoke external sharing | SharePoint Online | SharePoint Admin | Protect data from ex-user access
Security & Monitoring | Audit recent login & activity | Microsoft Sentinel / Entra ID | Security Admin | Check for suspicious activity before deletion
| Remove access from SaaS apps & VPN | Conditional Access / Azure / VPN | Security Admin | Prevent lateral access
Compliance & Documentation | Confirm offboarding completion | Internal HR / IT | HR / IT | Maintain offboarding records for audits

## BOM 1
Enterprise Model Single license → Microsoft 365 E5
Component | License | Price/User/Month | Users | Monthly Cost
Productivity + Security Suite | Microsoft 365 E5 | $57 | 200 | $11,400
Included features in E5:
Entra ID P2
Defender for Endpoint
Defender for Office 365
Defender for Cloud Apps
Intune
Additional Security Services
Component | Service | Monthly Cost
SIEM Monitoring | Microsoft Sentinel | $300
Log Storage | Azure Log Analytics | $150
Secrets Management | Azure Key Vault | $50
SOC Monitoring Service | Security Monitoring | $750
E5 Cost Summary
Cost Type | Monthly Cost | Annual Cost
Microsoft 365 E5 Licenses | $11,400 | $136,800
Security Monitoring | $1,250 | $15,000
Total Monthly Cost: $12,650
Total Annual Cost: $151,800
One-Time Setup Cost (E5 Model)
Activity | Cost
Tenant Security Configuration | $1,500
Email Migration | $2,500
Conditional Access Setup | $1,000
Endpoint Security Deployment | $900
Security Policy Configuration | $800
Sentinel Deployment | $1,200
Total Setup Cost: $7,900
Operational Services Cost
Service | Cost
Daily Security Monitoring | $25/day
Weekly Security Review | $150/week
User Onboarding | $15/user
User Offboarding | $5/user
Documentation & SOP Development Cost
Activity | Description | Cost (One-Time)
Security Architecture Documentation | Complete documentation of Phase 1–3 Zero Trust deployment architecture, including network design, controls, and security layers | $800
Operational Runbooks | Step-by-step procedures for daily operations, weekly checks, and incident response handling | $600
Security SOP Documentation | Standard Operating Procedures (SOPs) for Security Operations (SecOps) team activities and workflows | $500
Compliance Documentation | Security policies and documentation aligned with ISO 27001 controls and audit requirements | $500

## BOM 2
Cost Optimized Model Start with E3 / Business Premium Add security phase-by-phase
Phase 1 — Identity + Device Security
Component | License | Price/User/Month | Users | Monthly Cost
Microsoft 365 Base Productivity | Microsoft 365 E3 | $36 | 200 | $7,200
Identity Protection | Entra ID P2 | $9 | 200 | $1,800
Device Management | Microsoft Intune | Included E3 | 200 | $0
Endpoint Security | Defender for Endpoint P2 | $5.20 | 200 | $1,040
Phase 2 — Application & Data Protection
Component | License | Price/User/Month | Users | Monthly Cost
Email Threat Protection | Defender for Office 365 P1 | $2 | 200 | $400
CASB | Defender for Cloud Apps | $3.50 | 200 | $700
Secure App Access | Entra Application Proxy | Included | 200 | $0
Phase 3 — Security Monitoring & SOC
Component | License | Price | Quantity | Monthly Cost
SIEM Platform | Microsoft Sentinel | $300 | Tenant | $300
Log Storage | Azure Log Analytics | $150 | Tenant | $150
Threat Monitoring | Security Operations Monitoring | $750 | SOC | $750
Phase-wise License Cost Summary
Phase | Monthly Cost | Annual Cost
Phase 1 | $10,040 | $120,480
Phase 2 | $1,100 | $13,200
Phase 3 | $1,200 | $14,400
Total Monthly Cost: $12,340
Total Annual Cost: $148,080
One-Time Setup & Deployment Cost
Implementation Activity | Cost
Microsoft 365 Tenant Setup | $1,500
Email Migration (200 users) | $2,500
Identity Security Architecture Setup | $1,200
Conditional Access Deployment | $1,000
Intune Device Enrollment Setup | $900
Endpoint Security Deployment | $900
CASB Configuration | $800
Sentinel SIEM Setup | $1,200
Security Monitoring Playbook Creation | $700
Operational Services Cost
Service | Cost
Daily Security Monitoring | $25/day
Weekly Security Review | $150/week
User Onboarding | $15/user
User Offboarding | $5/user
Documentation & SOP Development Cost
Activity | Description | Cost (One-Time)
Security Architecture Documentation | Complete documentation of Phase 1–3 Zero Trust deployment architecture, including network design, controls, and security layers | $800
Operational Runbooks | Step-by-step procedures for daily operations, weekly checks, and incident response handling | $600
Security SOP Documentation | Standard Operating Procedures (SOPs) for Security Operations (SecOps) team activities and workflows | $500
Compliance Documentation | Security policies and documentation aligned with ISO 27001 controls and audit requirements | $500